## Test_case
|  | Product Name | shajgoj | TC Start Date | 2026-05-20 | TC Execution Start Date | _ _ |  |  |  |  | TEST CASE
|  | Module Name | Cart, Checkout, Search, Filter | TC End Date | 2026-08-20 | TC Execution End Date | _ _ |  |  |  |  | PASS | 72 | Funtional Testing
|  | Epic |  | Test Case developed By | Tasmin Jannat Tahsin | Browser (tested) | Yes |  |  |  |  | FAIL | 7 | UI Testing
|  | Developer Name(TL) |  | Test Case reviewed By | xx | Performance (tested) | Yes |  |  |  |  | NO RUN | 2 | Integration Testing
|  | Test Executed By | [9 empty] | BLOCKED | 0 | Regression Testing
[12 empty] | TOTAL | 82 | Performance Testing
SL | Test Case ID | Type of Testing | Features | Test Cases | Expected Result | Actual Result | Test Data | Reproducing Steps | Test Steps | Bugs screen shot | Dev Comments | Test Status | Remarks | Usability Testing
1 | Cart_001 | Browser compatibility Testing | Cart | Verify that that the website run crome and firefox browser | The website should be run | As Expected Result | Browsers-Chrome, Mozilla Firefox,Edge,Safari | 1. Go to Respective browsers. 2. Search 'shop.shajgoj.com' 3. Go to the website. | 1. Go to respective browsers. 2. Search 'shajgoj.com' 3. Go to the website. | N/A |  | PASS
2 | Cart_002 | Funtional Testing |  | Verify Add product to cart | Product is added successfully to the cart | As Expected Result | N/A | 1.Open browser 2.go to shop.shajgoj.com 3.Login with Phone Number 4.Put OTP for verification | 1.Select a product and click "Add to Cart" | N/A |  | PASS
3 | Cart_003 | Funtional Testing |  | Verify Add multiple products to cart | All selected products should be added to the cart successfully | As Expected Result | N/A |  | 1.choice different products and click "Add to Cart" one by one | N/A |  | PASS
4 | Cart_004 | Funtional Testing |  | Verify Add same product multiple times | Quantity increases or product should be updated as per requirements | As Expected Result | N/A |  | 1.Add the same product repeatedly | N/A |  | PASS
5 | Cart_005 | Funtional Testing |  | Verify cart icon count | Cart count should be updated correctly | Cart icon does not update the item count when the quantity of the same product is increased | N/A |  | 1.Add products to cart 2.Or add same product muitiple items to cart by increasing quantity | Bug_001 |  | FAIL | Total quantity should be display in cart icon to remove user confusion about their added items.
6 | Cart_006 | Funtional Testing |  | Verify product details in cart page | Correct product details(image,name,price) should be displayed | As Expected Result | N/A |  | 1.Add products to cart 2.Go to cart page 3.Check product name and image matches selected Product 4.Check product price is displayed correctly | N/A |  | PASS
7 | Cart_007 | Funtional Testing |  | Verify increase and decrease quantity | Quantity increases or decrease correctly and total updates also correctly | As Expected Result | N/A |  | 1.Add products to cart 2.Go to cart page 3.Click "+" button for increase quantity 4.Click "-" button for decrease quantity | N/A |  | PASS
8 | Cart_008 | Funtional Testing |  | Verify Remove Product from cart | Item should be removed successfully and Appropriate empty cart message should be displayed | As Expected Result | N/A |  | 1.Add products to cart 2.Go to cart page 3.Click remove/delete button | N/A |  | PASS
9 | Cart_009 | Funtional Testing |  | Verify Remove all Product from cart | Cart should be empty | As Expected Result | N/A | 1.Open browser 2.go to shop.shajgoj.com 3.Login with Phone Number 4.Put OTP for verification | 1.Add products to cart 2.Go to cart page 3.Click on remove/delete button | N/A |  | PASS
10 | Cart_010 | Funtional Testing |  | Verify subtotal calculation | Subtotal should be calculated correctly | As Expected Result | N/A |  | 1.Add products to cart 2.Go to cart page 3. Increase quantity 4.Check subtotal | N/A |  | PASS
11 | Cart_011 | Funtional Testing |  | Verify shipping charge calculation | Shipping cost is calculated correctly | As Expected Result | N/A |  | 1.Add products to cart 2.Go to cart page 3.Check shipping cost | N/A |  | PASS
12 | Cart_012 | Funtional Testing |  | Verify discount system in a specific product | Discount calculation should be applied successfully | As Expected Result | valid coupon code(if have) |  | 1.Add products to cart 2.Go to cart page 3.put valid coupon code(if have) 4. Check subtotal adding discount | N/A |  | PASS
13 | Cart_013 | Funtional Testing |  | Verify Continue shopping or start shopping option in cart page | User should beredirected to product page | As Expected Result | N/A |  | 1.Add products to cart 2.Go to cart page 3.Click "Continue Shopping"/"Start Shopping" | N/A |  | PASS
14 | Cart_014 | Funtional Testing |  | Verify proceed to checkout | User should be redirected to checkout page | As Expected Result | N/A | 1.Open browser 2.go to shop.shajgoj.com 3.Login with Phone Number 4.Put OTP for verification | 1.Add products to cart 2.Go to cart page 3.Click "Checkout"/"Proceed" | N/A |  | PASS
15 | Cart_015 | Funtional Testing |  | Verify add quantity beyond stock limit and maximum quantity limit | Appropriate message shouid be displayed | As Expected Result | N/A |  | 1.Add products to cart 2.Go to cart page 3.Enter quantity greater than stock or Add maximum allowed quantity | N/A |  | PASS
16 | Cart_016 | UI Testing |  | Verify cart page responsiveness | Layout should be displayed correctly | As Expected Result | N/A |  | 1.Add products to cart 2.Go to cart page 3. Open cart on mobile/tablet/desktop | N/A |  | PASS
17 | Cart_017 | UI Testing |  | Verify cart icon responsiveness | Cart icon should be displayed correctly | Cart icon does not visible by floating on mobile devices like desktop,laptop. | N/A |  | 1.Add products to cart 2.Go to cart page 3. Find flaoting cart icon on mobile screen | Bug_002 |  | FAIL | Cart icon should be visibled by floating correctly mobile screen for better user experience.
18 | Cart_018 | Funtional Testing |  | Verify stock availability | Appropriate message shouid be displayed | As Expected Result | N/A |  | 1.Add products to cart 2.Go to cart page 3.Add out-of-stock item | N/A |  | PASS
19 | Cart_019 | Funtional Testing |  | Verify cart persistence | The shopping cart retains the products a user has added even after certain events, such as refreshing the page, logging out, closing the browser, or switching devices | As Expected Result | N/A |  | 1.Add products to cart 2.Go to cart page 3.Refreshing the page,logging out, closing the browser, or switching devices | N/A |  | PASS
20 | Cart_020 | Funtional Testing |  | Verify empty cart | Navigation button should be displyed and works correctly (suppose click "Return to Shop" button ) | As Expected Result | N/A |  | 1.Add products to cart 2.Go to cart page 3.Remove selected product from cart page 4.Find Navigation option to return for shopping | N/A |  | PASS
21 | CHK_001 | Funtional Testing | Checkout | Verify access checkout page | Checkout page shouid be opened successfully | As Expected Result | N/A | 1.Open browser 2.go to shop.shajgoj.com 3.Login with Phone Number 4.Put OTP for verification | 1.Add products to cart 2.Go to cart page 3. Click "Proceed to Checkout" from cart | N/A |  | PASS
22 | CHK_002 | Funtional Testing |  | Verify checkout with items in cart | User can continue checkout process | As Expected Result | N/A |  | 1.Add products to cart 2.Go to cart page 3.Add products and proceed to checkout | N/A |  | PASS
23 | CHK_003 | Funtional Testing |  | Verify checkout with empty items in cart | Appropriate error message should be displayed | Checkout option not visible in cart Page | N/A |  | 1.Add products to cart 2.Go to cart page 3.Click proceed to checkout without product in cart | N/A |  | PASS
24 | CHK_004 | Funtional Testing |  | Verify billing address fields and Enter valid billing details | 1.All required billing fields are displayed 2.Details should be accepted successfully | As Expected Result | Name,Phone,City,Area,Address |  | 1.Add products to cart 2.Go to cart page 3.Go to checkout page. 4.Fill with valid details | N/A |  | PASS
25 | CHK_005 | Funtional Testing |  | Verify Leave mandatory fields blank | Appropriate error message should be displayed | As Expected Result | N/A |  | 1.Add products to cart 2.Go to cart page 3.Go to checkout page. 4.Submit checkout form | N/A |  | PASS
26 | CHK_006 | Funtional Testing |  | Verify shipping method selection | Shipping cost updates correctly | As Expected Result | N/A |  | 1.Add products to cart 2.Go to cart page 3.Go to checkout page. 3.Select shipping method 4.Submit checkout form | N/A |  | PASS
27 | CHK_007 | Funtional Testing |  | Verify shipping address option | Shipping address form should be displayed | Shipping Address is same with Billing Address | N/A |  | 1.Add products to cart 2.Go to cart page 3.Go to checkout page. 4.Select shipping method | N/A |  | PASS
28 | CHK_008 | Integration Testing |  | Verify use same billing and shipping addres | Shipping Address is same with Billing Addres in one form | As Expected Result | N/A |  | 1.Add products to cart 2.Go to cart page 3.Go to checkout page. 4.Check "Same as Billing Address" | N/A |  | PASS
29 | CHK_009 | Funtional Testing |  | Verify required field "Name " with entering invalid value | Appropriate error message should be displayed | As Expected Result | Ta78 |  | 1.Add products to cart 2.Go to cart page 3.Go to checkout page. 4.Enter invalid information in "Name" field | N/A |  | PASS
30 | CHK_010 | Funtional Testing |  | Verify required field "Phone " with entering invalid value | Appropriate error message should be displayed | As Expected Result | 1675 |  | 1.Add products to cart 2.Go to cart page 3.Go to checkout page. 4.Enter invalid value in "Phone" field | N/A |  | PASS
31 | CHK_011 | Funtional Testing |  | Verify required field "Select City" without selecting city | Appropriate error message should be displayed | As Expected Result | N/A |  | 1.Add products to cart 2.Go to cart page 3.Go to checkout page. 4.Click "Place order without selecting city | N/A |  | PASS
32 | CHK_012 | Funtional Testing |  | Verify required field "Select Area" without selecting city | Appropriate error message should be displayed | As Expected Result | N/A |  | 1.Add products to cart 2.Go to cart page 3.Go to checkout page. 4Click "Place order without selecting Area | N/A |  | PASS
33 | CHK_013 | Funtional Testing |  | Verify required field "Address" with entering invalid information | Appropriate error message should be displayed | As Expected Result | *89njjroad |  | 1.Add products to cart 2.Go to cart page 3.Go to checkout page. 4.Enter invalid address informatiom in "Address" field | N/A |  | PASS
34 | CHK_014 | Funtional Testing |  | Verify required field "Email" with entering invalid address | Appropriate error message should be displayed | As Expected Result | tahsin132@.com |  | 1.Add products to cart 2.Go to cart page 3.Go to checkout page. 4.Enter invalid email address in "Email" field | N/A |  | PASS
35 | CHK_015 | Funtional Testing |  | Verify payment method options | All available payment methods are displayed | As Expected Result | N/A |  | 1.Add products to cart 2.Go to checkout page 3.View payment section | N/A |  | PASS
36 | CHK_016 | Funtional Testing |  | Verify cash on delivery option | Order is placed successfully | As Expected Result | N/A |  | 1.Add products to cart 2..Go to checkout page 3.Select COD and place order | N/A |  | PASS
37 | CHK_017 | Funtional Testing |  | Verify payment system using credit/debit card | Payment is processed successfully | As Expected Result | N/A |  | 1.Add products to cart 2.Go to checkout page 3.Enter valid card details | N/A |  | PASS
38 | CHK_018 | Funtional Testing |  | Verify payment system using invalid credit/debit card | Validation message should be displayed | As Expected Result | N/A |  | 1.Add products to cart 2.Go to checkout page 3.Enter invalid card details | N/A |  | PASS
39 | CHK_019 | Funtional Testing |  | Verify online payment gateway | User is redirected to payment gateway | As Expected Result | N/A |  | 1.Add products to cart 2..Go to checkout page 3.Select online payment | N/A |  | PASS
40 | CHK_020 | Funtional Testing |  | Verify order summary | Correct products, quantity, and prices are displayed | As Expected Result | N/A |  | 1.Add products to cart 2..Go to checkout page 3.Review order details | N/A |  | PASS
41 | CHK_021 | Funtional Testing |  | Verify subtotal calculation | Subtotal is calculated correctly | As Expected Result | N/A |  | 1.Add products to cart 2..Go to checkout page 3.Check order summary | N/A |  | PASS
42 | CHK_022 | Funtional Testing |  | Verify discount calculation | Discount is reflected in total amount | As Expected Result | N/A |  | 1.Add products to cart 2.Go to checkout page 3.Apply coupon before checkout | N/A |  | PASS
43 | CHK_023 | Funtional Testing |  | Verify Place order successfully | Order confirmation is displayed | As Expected Result | N/A |  | 1.Add products to cart 2.Go to checkout page 3.Complete all steps and click "Place Order" | N/A |  | PASS
44 | CHK_024 | Funtional Testing |  | Verify order confirmation email | Confirmation email is sent | As Expected Result | N/A |  | 1.Add products to cart 2..Go to checkout page 3.Complete all steps and click "Place Order" | N/A |  | PASS
45 | CHK_025 | Funtional Testing |  | Verify Duplicate order prevention | Only one order is created | As Expected Result | N/A |  | 1.Add products to cart 2..Go to checkout page 3.Click "Place Order" multiple times | N/A |  | PASS
46 | CHK_026 | UI Testing |  | Verify mobile responsiveness | Checkout page displays correctly | As Expected Result | N/A |  | 1.Add products to cart 2..Go to checkout page 3.Complete all steps and click "Place Order" | N/A |  | PASS
47 | CHK_027 | Funtional Testing |  | Verify guest checkout | Guest user can place an order (if supported) | As Expected Result | N/A |  | 1.Add products to cart 2.Go to checkout page 3.Checkout without login | N/A |  | PASS
48 | CHK_028 | Funtional Testing |  | Verify navigation from checkout page to item page when selected products remove intentionaly(suppose click "Return to Shop" button and your card is empty) | Navigation button should be displyed and works correctly | As Expected Result | N/A |  | 1.Add products to cart 2.Go to checkout page 3.Remove selected product from cart page 4.Find Navigation option to return for shopping | N/A |  | PASS
49 | SRCH_001 | Funtional Testing | Search | Verify search with valid keyword | Relevant search results should be displayed | As Expected Result | N/A | 1.Open browser 2.go to shop.shajgoj.com | 1.Enter a valid keyword and click Search | N/A |  | PASS
50 | SRCH_002 | Funtional Testing |  | Verify search with exact product/item name | Matching result should be displayed | As Expected Result | N/A |  | 1.Enter exact name and search | N/A |  | PASS
51 | SRCH_003 | Funtional Testing |  | Verify search with partial keyword | Relevant results containing the partial keyword should be displayed | As Expected Result | N/A |  | 1.Enter partial text and search | N/A |  | PASS
52 | SRCH_004 | Funtional Testing |  | Verify search with uppercase letters | Search result should be displayed | As Expected Result | N/A |  | 1.Enter keyword in uppercase | N/A |  | PASS
53 | SRCH_005 | Funtional Testing |  | Verify search with lowercase letters | Search results are displayed correctly | As Expected Result | N/A |  | 1.Enter keyword in lowercase | N/A |  | PASS
54 | SRCH_006 | Funtional Testing |  | Verify search with mixed case letters | Search should be case-insensitive and display correct results | As Expected Result | N/A |  | 1.Enter keyword in mixed case | N/A |  | PASS
55 | SRCH_007 | Funtional Testing |  | Verify search with numbers | Relevant results are displayed Or " No results found" message displayed | As Expected Result | N/A |  | 1.Enter numeric value | N/A |  | PASS
56 | SRCH_008 | Funtional Testing |  | Verify search with alphanumeric value | Appropriate messages should be displayed | As Expected Result | N/A |  | 1.Enter alphanumeric keyword | N/A |  | PASS
57 | SRCH_009 | Funtional Testing |  | Verify search with special characters | Validation message or no results displayed | As Expected Result | N/A |  | 1.Enter special characters only | N/A |  | PASS
58 | SRCH_010 | Funtional Testing |  | Verify search with blank field | An appropriate validation message is displayed (e.g., "Please enter a search term.") or no search is performed. | Not Working | N/A |  | 1.Click Search without entering text | Bug_003 |  | FAIL
59 | SRCH_011 | Funtional Testing |  | Verify search with spaces only | Validation message appears or no results displayed | Not Working | N/A |  | 1.Enter spaces and search | Bug_004 |  | FAIL
60 | SRCH_012 | Funtional Testing |  | Verify search with leading and trailing spaces | Spaces are trimmed and results displayed correctly | As Expected Result | N/A |  | 1.Enter spaces before keyword 2.Enter spaces after keyword | N/A |  | PASS
61 | SRCH_013 | Funtional Testing |  | Verify search result sorting | Results appear in expected order | Not Working | N/A |  | 1.Observe displaying result after sorting | Bug_005 |  | FAIL
62 | SRCH_014 | UI Testing |  | Verify mobile search functionality | Search works correctly | As Expected Result | N/A |  | 1.Search from mobile device | N/A |  | PASS
63 | SRCH_015 | Funtional Testing |  | Verify search field placeholder | Appropriate placeholder text is displayed | As Expected Result | N/A |  | 1.View search box | N/A |  | PASS
64 | SRCH_016 | Usability Testing |  | Verify search suggesstions | Displays recommended search terms or results while a user is typing in the search box. | As Expected Result | N/A |  | 1.Types one or more letter of your item and check remmended result | N/A |  | PASS
65 | SRCH_017 | Usability Testing |  | Verify search Performance | Results load within acceptable time | As Expected Result | N/A |  | 1.Search and apply filter on large dataset | N/A |  | PASS
66 | FIL_001 | Funtional Testing | Filter | Verify filter section visibility | Filter options are displayed correctly | As Expected Result | N/A | 1. Open Browser 2.Go to shop.shajgoj.com | 1.Filter options are displayed correctly | N/A |  | PASS
67 | FIL_002 | Funtional Testing |  | Verify filter persistence | Filters remain applied according to requirements | As Expected Result | N/A |  | 1.Refresh the page after applying filters | N/A |  | PASS
68 | FIL_003 | Funtional Testing |  | Verify category filter | Only items from the selected category are displayed | As Expected Result | N/A |  | 1.Select a category | N/A |  | PASS
69 | FIL_004 | Funtional Testing |  | Verify minimum price value | Relevant results are displayed | As Expected Result | N/A |  | 1.Enter minimum valid price | N/A |  | PASS
70 | FIL_005 | Funtional Testing |  | Verify maximum price value | Relevant results are displayed | As Expected Result | N/A |  | 1.Enter maximum valid price | N/A |  | PASS
71 | FIL_006 | Funtional Testing |  | Verify invalid price range | Validation message is displayed | N/A | N/A |  | 1. Enter a invalid price | N/A |  | NO RUN
72 | FIL_007 | Funtional Testing |  | Verify brand filter | Only products from the selected brand are displayed | As Expected Result | N/A |  | 1.Select a brand | N/A |  | PASS
73 | FIL_008 | Funtional Testing |  | Verify multiple filters application and search combination | Results match both search term and filter criteria | As Expected Result | N/A |  | 1.Search and apply filters | N/A |  | PASS
74 | FIL_009 | UI Testing |  | Verify filter selection indicator | Selected filter is highlighted or marked | As Expected Result | N/A |  | 1.Apply a filter | N/A |  | PASS
75 | FIL_010 | Funtional Testing |  | Verify dropdown filter | Results update accordingly | Not Working properly | N/A |  | 1.Select value from dropdown | Bug_006 |  | FAIL | All types of filter should worked properly for better user experience
76 | FIL_011 | Funtional Testing |  | Verify checkbox filter | Results update correctly | As Expected Result | N/A |  | 1.Select checkbox options | N/A |  | PASS
77 | FIL_012 | Funtional Testing |  | Verify filter state after login/logout | Filter state behaves according to requirements | As Expected Result | N/A |  | 1.Apply filter and login/logout | N/A |  | PASS
78 | FIL_013 | Usability Testing |  | Verify filter performance | Results load within acceptable time | As Expected Result | N/A |  | 1.Apply filters on large data set | N/A |  | PASS
79 | FIL_014 | Funtional Testing |  | Verify sorting with filters | Results are filtered and sorted correctly | Not Working properly | N/A |  | 1.Apply filter and check sorting results | Bug_007 |  | FAIL
80 | FIL_015 | UI Testing |  | Verify filter on mobile device | Filters work correctly and UI should be responsive | As Expected Result | N/A |  | 1.Open browser on mobile device 2.go https://shop.shajgoj.com/login 3.Apply filter on mobile device | N/A |  | PASS
81 | FIL_016 | Funtional Testing |  | Verify default filter state | Default filter settings are applied | As Expected Result | N/A |  | 1.Open page for first time | N/A |  | NO RUN
82 | FIL_017 | Funtional Testing |  | Verify clear all applied filters | User can clear all applied filters | As Expected Result | N/A |  | 1.Apply one or multiple Filters and then clear all applied filters | N/A |  | PASS

## Test_Scenarios
| Project Name: |  |  | shop.shajgoj.com
| Reference Document: |  |  | FRS
| Created By: |  |  | Tasmin Jannat Tahsin
| Creation Date: |  |  | 03.20.2026
Approval Date:
Test Scenario ID | Reference | Module Name | Test Scenario Description |  | Priority | Number of Test Cases
TS_001 |  | Cart | Validate the URL in different browser |  | P0 | 1
TS_002 |  |  | Validate the working of "Add to Cart" functionality |  | P1 | 4
TS_003 |  |  | Validate the working of "View Cart" functionality |  | P1 | 1 | Critical | P0
TS_004 |  |  | Validate the working of "Update Quantity" functionality |  | P1 | 1 | High | P1
TS_005 |  |  | Validate the working of "Remove Product" functionality |  | P1 | 2 | Medium | P2
TS_006 |  |  | Validate the working of "Price Calculation" functionality |  | P1 | 2 | Low | P3
TS_007 |  |  | Validate the working of "Discount" functionality |  | P1 | 1
TS_008 |  |  | Validate the working of "Cart Persistence" |  | P1 | 1
TS_009 |  |  | Validate the working of "Stock Validation" functionality |  | P2 | 2
TS_010 |  |  | Validate the working of "Guest User Cart" functionality |  | P3 | 1
TS_011 |  |  | Validate the working of "Navigation" functionality |  | P1 | 2
TS_012 |  |  | Validate the working of "Responsive Design" |  | P3 | 2
TS_013 |  |  | Validate the working of "Empty Cart" functionality |  | P1 | 1
TS_014 |  |  | Validate the working of "Checkout" functionality |  | P1 | 1
TS_015 |  | Checkout | Validate the working of "Checkout page Navigation" and "Responsiveness" |  | P2 | 5
TS_016 |  |  | Validate the working of "Billing and Shipping Addess Information" |  | P1 | 9
TS_017 |  |  | Validate the working of "Shipping Addess Method" |  | P1 | 2
TS_018 |  |  | Validate the working of "Order Summary" |  | P1 | 2
TS_019 |  |  | Validate the working of "Coupon/promo Code" |  | P1 | 1
TS_020 |  |  | Validate the working of "Paymenr Method" |  | P1 | 4
TS_021 |  |  | Validate the working of "Place Order" |  | P0 | 3
TS_022 |  |  | Validate the working of "Error Handling" |  | P1 | 2
TS_023 |  | Search | Validate the working of "Basic Search bar functionality" |  | P1 | 2
TS_024 |  |  | Validate the working of "Input Validation and Search Accuracy" |  | P3 | 7
TS_025 |  |  | Validate the working of "Search Suggestions" |  | P2 | 2
TS_026 |  |  | Validate the working of "Case Sensitivity" |  | P2 | 3
TS_027 |  |  | Validate the working of "Search Filters and Sorting" |  | P3 | 1
TS_028 |  |  | Validate the working of "Performance" |  | P3 | 1
TS_029 |  |  | Validate the working of "Responsiveness" |  | P1 | 1
TS_030 |  | Filter | Validate the working of "Filter Availability" |  | P2 | 8
TS_031 |  |  | Validate the working of "Filter Selection" |  | P1 | 2
TS_032 |  |  | Validate the working of "Filter Performance" |  | P1 | 1
TS_033 |  |  | Validate the working of "Filter Persistence And Responsiveness" |  | P3 | 3
TS_034 |  |  | Validate the working of "Sorting with Filters" |  | P3 | 1
TS_035 |  |  | Validate the working of "No Matching Results" |  | P3 | 1

## Bug_Report
Bug Report
BUG ID: Cart_001
Date:
Title: Cart icon does not update the item count when the quantity of the same product is increased
Module: Cart
Bug Description:
When a user increases the quantity of the same product in the cart, the cart icon displays only one item instead of the total quantity selected. However, when the user adds two different products to the cart, the cart icon correctly displays the total number of items. This indicates that the cart icon counts unique products rather than the total product quantity.
Steps:
1.Open the website. 2.Select a product (e.g., Aveeno Baby sunscreen Lution). 3.Add the Product to the cart. 4.Increase the quantity of the Product from 1 to 3 using the quantity selector or "+" button. 5.Observe the cart icon count. 6.Clear the cart. 7.Add Aveeno Baby sunscreen Lution and Neutrogena sheer Zinc to the cart. 8.Observe the cart icon count again.
Environment: Production Server
Expected Result:
1.When the quantity of the same product is increased to 3, the cart icon should display 3. 2.When two different products are added (one quantity each), the cart icon should display 2.
Actual Result:
1.After increasing the quantity of the same product to 3, the cart icon still displays 1. 2.When two different products are added, the cart icon correctly displays 2.
Impact:
The incorrect cart count can confuse users about the number of items they have selected.An incorrect item count may reduce user confidence and lead to checkout mistakes.
Severity: Medium
Priority: High
Attachment:
1.Bug_screenshot
2.Bug_screenshot
Responsible QA: Tasmin Jannat Tahsin

## Test Plan
Full Test Plan Document
p

## Test_Summary_Report
Test Case Report
Project Name | shop.shajgoj.com
Module Name | Cart, Checkout, Search, Filter |  |  |  |  | Result
Test Case Version | 1 |  |  |  |  | Pass | 73 | New Feature :
Written By | Tasmin Jannat Tahsin |  |  |  |  | Fail | 7 | Testing Scope :
Executed By | Tasmin Jannat Tahsin |  |  |  |  | No Run | 2 | Testing Environment:
Reviewed By | [5 empty] | Out of Scope | 0
TEST EXECUTION REPORT
Test Case | PASS | FAIL | Not Executed | Out Of Scope | Total Test Case
| 73 | 7 | 2 | 0 | 82
Grand Total | 73 | 7 | 2 | 0 | 82
LIMITATIONS
Documents |  |  |  | Received | Useful
PRD |  |  |  | No | No
USER STORY |  |  |  | No | No
| Testing Type in Scope | Description
Yes/ No. Justification (If No): | Functional Testing | This type of testing ignores the internal parts and focuses only on the output to check if it is as per the requirement or not.
Yes/ No. Justification (If No): | Integration Testing | Testing of all integrated modules to verify the combined functionality after integration is termed as Integration Testing.
Yes/ No. Justification (If No): | Negative Testing | Testing having the mindset of “attitude to break” using incorrect data and invalid inputs.
Yes/ No. Justification (If No): | Usability Testing | Test application from user friendliness perspective.
Yes/ No. Justification (If No): | Browser Compatibility Testing | Browser Compatibility Testing is performed for web applications and it ensures that the software can run with the combination of different browser and operating system. This type of testing also validates whether web application runs on all versions of all browsers or not.
Yes/ No. Justification (If No): | Boundary Value Testing | There is an upper and lower boundary for each range and testing is performed on these boundary values.
Yes/ No. Justification (If No): | Risk Based Testing | Risk-Based Testing includes testing of highly critical functionality, which has the highest impact on business and in which the probability of failure is very high.
Yes/ No. Justification (If No): | Regression Testing | Testing an application as a whole for the modification in any module or functionality is termed as Regression Testing.

## RTM
Requirements Traceability Matrix
Requirement ID | Module | Requirement Description | TC ID | Test Case | Priority | Status
RQ_001 | Cart | User can add products to the cart | Cart_002 | Verify Add product to cart | High | Pass | Pass
RQ_002 |  | User can update product quantity | Cart_007 | Verify increase and decrease quantity | High | Pass | Fail
RQ_003 |  | User can remove products from cart | Cart_008 | Verify Remove Product from cart | High | Pass
|  |  | Cart_009 | Verify Remove Product from cart | High | Pass | No Run
RQ_004 |  | Cart icon displays correct item count | Cart_005 | Verify cart icon count | High | Fail | Blocked
RQ_005 |  | Cart persists after page refresh/login | Cart_019 | Verify cart persistence | Medium | Pass
RQ_006 | Checkout | User can proceed to checkout | CHK_001 | Verify access checkout page | High | Pass | Critical | P0
RQ_007 |  | User can enter shipping address | CHK_007 | Verify shipping address option | High | Pass
|  |  | CHK_008 | Verify use same billing and shipping addres | High | Pass | High | P1
RQ_008 |  | User can select shipping method | CHK_006 | Verify shipping method selection | High | Pass | Medium | P2
RQ_009 |  | User can select payment method | CHK_015 | Verify payment method options | High | Pass | Low | P3
RQ_010 |  | Order is placed successfully | CHK_023 | Verify Place Order successfully | Critical | Pass
RQ_011 | Search | User can search using valid keywords | SRCH_001 | Verify search with valid keyword | High | Pass
RQ_012 |  | Search with invalid keyword | SRCH_007 | Verify search with numbers | High | Pass
|  |  | SRCH008 | Verify search with alphanumeric value | Medium | Pass
RQ_013 |  | Search with empty input | SRCH_010 | Verify search with blank field | Medium | Fail
RQ_014 |  | Search is case-insensitive | SRCH_004 | Verify search with uppercase letters | Medium | Pass
|  |  | SRCH_005 | Verify search with lowercase letters | Medium | Pass
|  |  | SRCH_006 | Verify search with mixed case letters | Medium | Pass
RQ_015 |  | Search supports special characters handling | SRCH_009 | Verify search with special characters | Low | Pass
RQ_016 | Filter | User can filter products by category | FIL_003 | Verify category filter | High | Pass
RQ_017 |  | User can filter products by brand | FIL_007 | Verify brand filter | High | Pass
RQ_018 |  | User can filter products by price range | FIL_004 | Verify minimum price value | High | Pass
|  |  | FIL_005 | Verify maximum price value | High | Pass
|  |  | FIL_006 | Verify invalid price range | High | Pass
RQ_019 |  | User can apply multiple filters | FIL_008 | Verify multiple filters application and search combination | Medium | Pass
RQ_020 |  | Applied filter indicator is displayed | FIL_009 | Verify filter selection indicator | Medium | Pass
RQ_021 |  | User can clear all applied filters | FIL_017 | Verify clear all applied filters | Medium | Pass
RTM SUMMARY
|  | Modules | Requirements | Test Case
|  | Cart | 5 | 6
|  | Checkout | 5 | 6
|  | Search | 5 | 8
|  | Filter | 5 | 8
|  | ToTal | 20 | 28

## Test_Metrices
Test Metrics
#SL | Metrics | Description | Result (%)
1 | Percentage of Test Cases Executed | (No. of Test Cases Executed / Total no. of Test Cases Written) * 100 | (80/82)*100 = 97.6%
2 | Percentage of Test Cases Not Executed | (No. of Test Cases not Executed / Total no. of Test Cases Written) * 100 | (2/82)*100 = 2.4%
3 | Percentage of Test Cases Passed | (No. of Test Cases Passed / Total no. of Test Cases Executed) * 100 | (73/82)*100 = 89%
4 | Percentage of Test Cases Failed | (No. of Test Cases Failed / Total no. of Test Cases Executed) * 100 | (7/82)*100 = 8.5%
5 | Percentage of Test Cases Blocked | (No. of Test Cases Blocked / Total no. of Test Cases Executed) * 100 | (0/50)*100 = 0
6 | Defect Density | No. of Defects found / Size (No. of Requirements) | N/A
7 | Defect Removal Efficiency (DRE) | (Fixed Defects / (Fixed Defects + Missed Defects)) * 100 | N/A
8 | Defect Leakage | (No. of Defects found in UAT/ No. of Defects found in Testing) * 100 | N/A
9 | Defect Rejection Ratio | (No. of Defects Rejected/ Total no. of Defects Raised) * 100 | N/A
10 | Defect Age | Fixed date - Reported date | N/A
11 | Customer Satisfaction | No. of complaints per Period of Time | N/A

## Recommandation
GENERAL INFORMATION
Test stage | Unit performance | Functionality Regression |  | Integration Acceptance | System Pilot | Interface
Functionality,Integration,Interface
Date: | 2026-07-07 |  |  | System Date,If Applicable |  | mm/dd/yy
Tester: | Tasmin Jannat Tahsin |  |  | Test Case Number |  | 82
Test case Description: | The testing o focused on the Cart, Checkout, Search, and Filter modules to verify that the application's core functionalities met the specified requirements. Test cases were executed using both valid and invalid inputs to evaluate functional correctness, usability, and system behavior under different scenarios.
Results: | Pass:72 | Fail:07 | No Run:07 | Incident Number,If Applicable: |  | Specify the unique identifier assingned to the incident.
INTRODUCTION
Requirement(s) to be tested: | The system should allow users add product ,remove product,update quantity,correctly checkout,apply search and filter functionalities correctly. | [5 empty] | No of Requirements: 20
Roles and Responsibilites: | Describe each project team member and stakeholder involved in the test, and identify their associated responsibility for ensuring the test is executed appropriately
Set Up procedures: | 1.Launch the website. 2.Ensure the application is running correctly. 3.Log in with a valid user account . 4.Navigate to the Products page,Cart page,checkout page one by one. 5.Apply filter and check searching functionality.
Stop Procedures: | 1.Record the test result. 2.Capture screenshots if any defect is found. 3.Log defects in the bug-tracking system. 4.Close the browser. 5.Log out of the application.
ENVIRONMENTAL NEEDS
Hardware: | Laptop, 16GB RAM, Stable internet connection
Software: | Windows 11, Google Chrome (latest version), Mozilla Firefox (latest version), Microsoft Edge (latest version), Website under test (production environment)
Procedural Requirments: | 1.Test data must be available. 2.Website server must be operational. 3.User account must have permission to add products. 4.Internet connection should remain stable throughout testing
TEST
Test Items and Features: | Cart,Checkout,Search,Filter
Input Specifications: | Define each input required to execute the test case and reference any required relationship between inputs.
Procedural Steps: | Describe the sequence of actions necessary to prepare and execute the test case.Provide detailed testprocedures for each test case; explain precisely how each test case will be executed.
Expected Results of Case: | Describe the outcome anticipated from the test case.Specify the criteria to be used to determine whether the item has passed or failed.
ACTUAL RESULTS
Output Specifications: | Define all of the outputs and features required of the test case and provided expected values. While executing the test, record and describe the visually observable outputs as they occure.Produce tangible evedence of the output such as ascreen print. At the conclusion,discreancies between the expected results and the actual results.